## Slide 1
Timeline in the Preparation for the
Virtual Program Accreditation Visit
(Appendix C)
Philippine Accrediting Association of Schools, Colleges and Universities

## Slide 2
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
3 months before the survey visit | Form Survey Team and email the tentative line-up to the school Discuss Data Sharing Agreement with the School (Appendix L) | 1. PAASCU Secretariat 2. PAASCU Secretariat

## Slide 3
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2.5 months before the survey visit | Email the Secretariat the confirmation on the Survey Team line-up or request for any changes | School to be visited

## Slide 4
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 months before the survey visit | 1. Email the final Survey Team line-up to the school with the changes, if any | 1. PAASCU Secretariat

## Slide 5
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 months before the survey visit | 2. Email all Survey Team members the following: Non-Disclosure and Confidentiality Agreement (Appendix M) Code of Conduct and Policy on Conflict of Interest (Appendix N) Interview Photo and Video Consent Form (Appendix O) | 2. PAASCU Secretariat

## Slide 6
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 months before the survey visit | 3. Submit the following: Self-Survey Report and supporting materials using the digital storage facility of the school access information to the digital files access information to the LMS of courses on programs to be visited (b and c will be emailed to the PAASCU Secretariat) | 3. School to be visited

## Slide 7
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 months before the survey visit | 4. Email Survey Team of the submission and access information | 4. PAASCU Secretariat

## Slide 8
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
The 1st-2nd week after submission of the Self-Survey Report | 1. Review the Self-Survey Report and supporting materials and email any additional request for materials to the Survey Team Chair who will consolidate the same | 1. Survey Team and the PAASCU Secretariat

## Slide 9
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
The 1st-2nd week after submission of the Self-Survey Report | Email the consolidated request to PAASCU Secretariat Email the consolidated request to the school | 2. Survey Team Chair PAASCU Secretariat

## Slide 10
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
The 1st-2nd week after submission of the Self-Survey Report | Email the Secretariat the following: Completed Non-Disclosure and Confidentiality Agreement Form Completed Code of Conduct and Policy on Conflict of Interest Form Completed Interview Photo and Video Consent Form | 4. Survey Team

## Slide 11
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
The 3rd-4th week after submission of the Self-Survey report | 1. Submit requested materials through the digital file storage facility and email PAASCU of this submission including the access information | 1. School to be visited

## Slide 12
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
The 3rd-4th week after submission of the Self-Survey report | 2. Email Survey Team about the submission and access information | 2. PAASCU Secretariat

## Slide 13
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
1 month before the survey visit | 1. Email the PAASCU Secretariat the 2-day Visit Schedule (with the list of interviewees) | 1. Survey Team chair

## Slide 14
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
1 month before the survey visit | Email the school the following: Finalized schedule of the 2-day visit Template of interviewees Interviewee Photo and Video Consent Form | 2. PAASCU Secretariat

## Slide 15
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 weeks before the survey visit | 1. Email the Secretariat the following: Completed template of interviewees Plan of the live walk-through tour if any Access information to all classes Completed Photo and Video Consent Forms | 1. School to be visited

## Slide 16
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
2 weeks before the survey visit | 2. Email above items (except d) to the Survey Team | 2. PAASCU Secretariat

## Slide 17
Timeline in the Preparation for the Virtual Program Accreditation Visit
TIME | ACTIVITY | UNIT RESPONSIBLE
1 week before the survey visit | Final Readiness and Preparation Test | Accreditation Team, PAASCU Secretariat, School to be Visited (Head of Self-Survey Team and Technical Staff)

## Slide 18
Thank you!